## Sheet1
TPG Milestone Review
Milestone | Completed? | If No, Why?
Proposal | 2021-02-04
Use Cases | 2021-03-31
Requirements | 2021-03-31
SPMP | 2021-03-31
Duplicate Website Locally | 2021-04-20
Create Booking Tab | 2021-04-23
Implement Calendar | Not yet | Took more time than expected to get the website admin access and pull it down locally
Store Availability | Not yet | I do not predict this part to be too time consuming, as I have researched and selected tools
Allow Bookings | Not yet | ^
Store Bookings | Not yet | ^
Confirmation message and email | Not yet | ^
Website Release | Not yet | ^